## Cover Page
Retail Product Management System
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Manish Shingare , Dhriti Sinha, Prajwal Nirmal,Priyanka jatav,Himanshu Ranjan Singh,Ashi Agrawal
| Role | POD Members
Signature
| Date | 2022-06-29
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Project ID: <ADM22DF042> Product Backlog Retail Product Management System
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
1 | Welcome Page | USER | As a user of Retail Product Management System , I want to see the welcome page. | User shall see a welcome page displayed. | 1 | 3
2 | Show Login page with components | USER | As a user, I want to see the Login page with input fields , username and password and a login button. | User shall see the login components displayed in the login page | 1 | 3
3 | Login validation | USER | As a user, I want to submit the login credentials to the system, so the login fields should be validated | User should be able to click on the login button , user shall see the errors if occurs. | 1 | 3
4 | Login Success | USER | As a user, I want to see the Home Page. | User shall see his/her Home Page | 1 | 2
5 | Login Failure | USER | As a user, I should see an error message for invalid login credentials | User shall see an error message | 1 | 2
6 | Search by ProductId | USER | As a User, I want to search product by id | User will see the respective search product page | 1 | 3
7 | Search by ProductName | USER | As a User, I want to search product by name. | User will see the respective search product page. | 1 | 3
8 | Show Search product page and searching components | USER | As a user, I want to see the product Id input field in the search product page, so that I can provide my product id. | User shall see the searching components displayed in the serach product page. | 2 | 3
9 | Product ID Validation | USER | As a user , the enter id fields should be validated in the search product page. | User shall see validation errors if present | 2 | 3
10 | Show Add To Cart Page | USER | As a User,I shall see add to cart page. | user will see the respective add to cart page | 2 | 2
11 | Add to Cart components & validation | USER | As a user, I want to see the product id and customer id input field, zipcode field , delivery date field and add to cart button in the add to cart page, so that I can add a product and validate fields. | User shall see the add to cart components displayed in the page. | 2 | 3
12 | Item Added to Cart page | USER | As a user, I shall see my respective item added to cart Page | User shall see his/her respective Page | 2 | 2
13 | Show Out of stock Page | USER | As a user, I shall see add to wishlist out of stock page button in the out of stock page, so that I can add a product to wishlist. | User shall see the add to cart button displayed in the page. | 2 | 2
14 | Add to wishlist page | USER | As a user, I want to add item to wishlist, so that I can buy later. | User should be able to click on add item to wishlist button. | 2 | 2
15 | Show Rate a Product Page | USER | As a user, I want to see the rating page. | User shall see a rating page displayed. | 2 | 3
16 | Rating validation | USER | As a user , the rating fields should be validated in the rate a product page. | User shall see validation errors if present like please enter a value less than or equal to 5. | 2 | 2
17 | Rating Added Successfully | USER | As a user, I want to see rating added to product successfully. | User shall see a product rating . | 2 | 3

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000